## Summary
Group B1 - Sprint Tracker
Date | Time | Type | Topic(s) | Points | Remaining
2023-01-07 | 14:00 | In-person | - Developing User Stories - Sprint Meeting - Voted for Sprint points | 0 | 21 | Note: we did not track how many points per day but more the tasks within an item. The point estimates are based on a comparison of the work completed and item associated
2023-01-09 | 14:00 | In-person | - Sprint 1 Meeting - Work on tasks collaboratively | 2 | 19
2023-01-09 | 19:00 | In-person | - Refined our user story with Prof. - Voted for Sprint points | 0 | 36
2023-01-10 | 14:00 | In-person | - Sprint 1 Meeting - Work on tasks collaboratively - Developed the methodology - Prepared a start at the website and visual | 16 | 20
2023-01-11 | 15:00 | In-person | - Review feedback from class & prof - Sprint 2 Kick Offs | 2 | 18
2023-01-12 | 14:00 | In-person | - Storytime Meeting (attempted but ended up discussing other items) - Merged into a Sprint 2 Meeting | 0 | 18
2023-01-13 | 14:30 | In-person | - Sprint 2 Meeting and finalized the project requirements (as Aditi departed) | 18 | 0
2023-01-14 | N/A | Slack / Virtual | - Virtual consolidation of input for Sprint 2 retrospective (given time zones) | 0 | 0
Formulas:
Date = [Date, row above]
Date = [Date, row above]+1
Note on G5: We used the poker voting and assigned points
Note on F6: Completed the "About Us" page
Note on F7: Simple website and visuals prepared
Note on G7: We had a 2nd vote and amended the points
Note on F9: Finalized the methodology